## TIME MANAGEMENT Gantt Chart
TIME MANAGEMENT GANTT CHART TEMPLATE
[ MOVIE RECOMMENDATION SYSTEM ]
TASK NAME | START DATE | END DATE | DURATION (days)
Project Initiation | 2020-10-14 | 2020-10-30 | 17
Project Charter | 2020-10-14 | 2020-10-16 | 3
Projection & Research | 2020-10-19 | 2020-10-23 | 5
Stakeholder | 2020-10-21 | 2020-10-23 | 3
Guidelines & Developing a Business Case | 2020-10-26 | 2020-10-30 | 5
Project Planning | 2020-11-02 | 2020-11-12 | 11
Collect Requirements | 2020-11-02 | 2020-11-04 | 3
Define, Verify &Contol Scope | 2020-11-03 | 2020-11-08 | 6
Create WBS | 2020-11-09 | 2020-11-13 | 5
Project Execution | 2020-11-16 | 2020-12-29 | 44
Procurement Management | 2020-11-16 | 2020-11-24 | 9
Track and Task Management | 2020-11-25 | 2020-12-01 | 7
Project Tasks Execution | 2020-12-02 | 2020-12-08 | 7
KPI's Management | 2020-12-09 | 2020-12-15 | 7
Project Updates | 2020-12-16 | 2020-12-22 | 7
Chart Updates | 2020-12-23 | 2020-12-29 | 7
Project Implementation | 2020-12-30 | 2021-01-12 | 14
Installation | 2020-12-30 | 2021-01-06 | 8
Configuration | 2021-01-07 | 2021-01-13 | 7
Project Testing | 2021-01-14 | 2021-02-02 | 20
Unit Testing | 2021-01-14 | 2021-01-20 | 7
Run Testing | 2021-01-21 | 2021-01-27 | 7
Review Testing | 2021-01-28 | 2021-02-02 | 6
Project Closure | 2021-02-03 | 2021-02-10 | 8
Final Documentation | 2021-02-03 | 2021-02-05 | 3
Project Closure | 2021-02-05 | 2021-02-10 | 6